## Date (hidden)
Rig Payment (Conductor Piling)
Start date | End date
2026-05-03 | 2026-08-11 15:00 | 100.625
Rig Move
Start date | Present date
2026-04-23 | 2026-08-11 15:00 | 110.625
Spud Date | Present date
2026-05-09 10:00 | 2026-08-11 15:00 | 94.2083

## NPT
AWOBA NW 5: NPT TRACKING REGISTER
Date | Phase | Hours (hr) | Days | NPT Cost ($) | Description | Category | Responsible Party
2026-05-07 | Conductor Piling/Cleanout | 1 | 0.041667 | 11812.8202 | Operations delayed due to faulty stroke counter while running 23" Rotary BHA; system successfully troubleshot and repaired | Equipment Failure | SMS Joy
2026-05-07 | Conductor Piling/Cleanout | 1.5 | 0.0625 | 17719.2303 | Observed limited sea-water in pit, POOH 23" Bit 30"-CP Clean-Out Assy T/surface, brk/LD X/Os, 23" bit, bit sub. | Mud / Solids | Clinton
2026-05-11 | 17-1/2" x 23" Hole Section | 23.5 | 0.97917 | 261104.6878 | Investigated 250 psi pressure drop; tripped pipe (POOH/RIH) to inspect for drill string washouts and bit nozzle integrity. | Mechanical | TBD
2026-05-14 | 17-1/2" x 23" Hole Section | 11 | 0.45833 | 154575.8173 | Serviced TDS; replaced pipe handler rotating head hydraulic motor, repaired solenoid, and extended cutting chute. | Mechanical | SMS Joy
2026-05-19 | 17-1/2" x 23" Hole Section | 140 | 5.8333 | 1176243.3705 | Mitigated heavy backflow, cleaned out wellbore, and successfully engaged and recovered lost 18-5/8" x 20" casing joints using an ITCO spear fishing assembly; completed a 23" bit clean-out run to bottom prior to re-running casing | Human Error | Geowell
2026-05-27 | 17-1/2" x 23" Hole Section | 4.5 | 0.1875 | 58079.6079 | RD Bowel and C-Plate, cut both return lines on 18-5/8" above Rotary, cut false bushing support braces. Torch'd/cut-off flowlines on CP. Meanwhile wait for BOP slings to PU Casing to unset slips. | Equipment Failure | SMS Joy
2026-05-31 | 17-1/2" x 23" Hole Section | 9.5 | 0.39583 | 150768.8369 | Operation delayed due to low mud rheology in the 16" hole section; tripped BHA above casing shoe twice to treat, condition, and circulate drilling mud to specification. | Mud / Solids | Clinton
2026-05-31 | 16" Hole Section | 25 | 1.0417 | 307101.1358 | Investigated low standpipe pressure (600 psi @ 750 GPM); checked surface lines/strainers, then POOH to surface to inspect BHA. Laid down 16" mud motor assembly and transitioned to a 16" Rotary BHA pending backup equipment. | Mechanical | TBD
2026-06-05 | 16" Hole Section | 11 | 0.45833 | 135277.1236 | Short-tripped 16" PDC/MM BHA into casing shoe to change out and replace the TDS FH saver sub with an HT55 saver sub | Mechanical | SMS Joy
2026-06-13 | 16" Hole Section | 1.5 | 0.0625 | 18472.8298 | Worked on SCR gettting assignment, trouble shooting same & fixed the issue-Ok | Equipment Failure | SMS Joy
2026-06-18 | 16" Hole Section | 1 | 0.041667 | 16551.9432 | Changed out Existing FMS & replaced same with back up FMS -OK. | Equipment Failure | Mega Field
2026-06-19 | 16" Hole Section | 1.5 | 0.0625 | 25995.3554 | Repaired faulty cement head down valve. Dropped bottom plug. Commenced pumping 12.5 ppg lead slurry. Fixed engine fan belt after unit shutdown. | Cementing | MultiChase
2026-06-22 | 16" Hole Section | 4 | 0.16667 | 40590.6669 | Attempted to pressure test casing againt cement to 500psi observed & observed leakage from CHH, Well head engineer work on CHH & Re-tightened CHH bolts-OK. | Wellhead | Ulla
2026-06-27 | 12 1/4" Hole Section | 112.5 | 4.6875 | 1384151.7725 | Encountered a tight spot while pulling out of hole (POOH), performed rig maintenance on the standpipe, IBOP, and TDS, then suffered a pressure spike and lost returns upon running back in hole (RBIH), which required working the stuck string for several hours until pipe movement and full fluid returns were successfully restored before pumping a high-viscosity sweep. | Equipment Failure | SMS Joy
2026-07-04 | 12 1/4" Hole Section | 0.5 | 0.020833 | 6175.9167 | TDS hydraulic hose leakage | Equipment Failure | SMS Joy
2026-07-05 | 12 1/4" Hole Section | 2.5 | 0.10417 | 30889.5833 | TDS hydraulic hose leakage | Equipment Failure | SMS Joy
2026-07-05 | 12 1/4" Hole Section | 1 | 0.041667 | 12355.8333 | Mud pump swab leakage | Equipment Failure | SMS Joy
2026-07-12 | 12 1/4" Hole Section | 3 | 0.125 | 36414.125 | Attempted to test the bonnet seal, obs'd hydraulic leakage from Annular BOP, troubleshoot fault and obs'd that the plug of the annular BOP drain pulled out fixed the fault. Carried out bonnet test against test plug and annular to 1500psi- ok and POOH test plug. | Equipment Failure | SMS Joy
2026-07-26 | Perforation and Wellbore Cleanout | 1 | 0.041667 | 11273.2671 | Attempted to cont. RIH, Observed faulty brakes/Broken Draw-work caliper pin. Troubleshoot/Fixed same, Ok. | Equipment Failure | SMS Joy
2026-07-29 | Completions | 3.5 | 0.14583 | 39456.4347 | Observed Draw-works Low Clutch-Drive chain faulty, Troubleshoot/Fixed Same while cont. monitor well on TT. Loss Rate: 10BBLs/Hr. | Equipment Failure | SMS Joy

## Metrics (hidden)
[5 empty] | Month | NPT (Hrs) | NPT Cost ($) |  |  |  | Category | Sum of Hours (hr) |  |  | Responsible Party | Sum of Hours (hr) |  |  | Phases | Sum of Hours (hr)
KPI |  |  |  |  | 2026-05-01 | 216 | 2137405.5066 |  |  |  | Human Error | 140 | Human Error | 140 | Clinton | 11 | Clinton | 11 | Conductor Piling/Cleanout | 2.5 | Conductor Piling/Cleanout | 2.5
Total Rig Hours | 2415 | hrs | 100.625 | days | 2026-06-01 | 143 | 1621039.6915 |  |  |  | Equipment Failure | 132 | Equipment Failure | 132 | Geowell | 140 | Geowell | 140 | 17-1/2" x 23" Hole Section | 188.5 | 17-1/2" x 23" Hole Section | 188.5
Total NPT Hours | 359 | hrs | 14.9583 | days | 2026-07-01 | 11.5 | 136565.1602 |  |  |  | Mechanical | 70.5 | Mechanical | 70.5 | SMS Joy | 153 | SMS Joy | 153 | 16" Hole Section | 44 | 16" Hole Section | 44
Overall NPT % | 14.87% | [9 empty] | Mud / Solids | 11 | Mud / Solids | 11 | TBD | 48.5 | TBD | 48.5 | 12 1/4" Hole Section | 119.5 | 12 1/4" Hole Section | 119.5
Total NPT Cost ($) | 3895010.3583 | [9 empty] | Wellhead | 4 | Wellhead | 4 | Mega Field | 1 | Mega Field | 1 | Perforation and Wellbore Cleanout | 1 | Perforation and Wellbore Cleanout | 1
Productive Hours | 2056 |  | 85.6667 | days | [6 empty] | Cementing | 1.5 | Cementing | 1.5 | MultiChase | 1.5 | MultiChase | 1.5 | Completions | 3.5 | Completions | 3.5
Productive Time (%) | 85.13% | [13 empty] | Ulla | 4 | Ulla | 4
[5 empty] | Category | Sum of Hours (hr) | Sum of NPT Cost ($)
[5 empty] | May | 216 | 2137405.5066 | May | 216 | 2137405.5066
[5 empty] | Jun | 131.5 | 1621039.6915 | Jun | 131.5 | 1621039.6915
[5 empty] | Jul | 11.5 | 136565.1602 | Jul | 11.5 | 136565.1602
Formulas:
NPT (Hrs) = SUMIFS(NPT[Hours (hr)], NPT[Date], ">=" & [Month], NPT[Date], "<=" & EOMONTH([Month],0))
NPT (Hrs) = SUMIFS(NPT[Hours (hr)], NPT[Date], ">=" & [Month], NPT[Hours (hr)], "<=" & EOMONTH([Month],0))
NPT Cost ($) = SUMIFS(NPT[NPT Cost ($)], NPT[Date], ">=" & [Month], NPT[Date], "<=" & EOMONTH([Month],0))

## Dashboard
AWOBA NW 5: NPT DRILLING PERFORMANCE DASHBOARD
`
AWOBA NW-5 NPT ANALYSIS | Overview
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Total Rig Time
2,415
hrs |
100.6
days
Total NPT
359.0
hrs |
15.0
days
Productive Time
2,056.0
hrs |
85.7
days
Total NPT Cost ($)
3,895,010.36
Overall NPT (%)
14.87%
Productive Hours (%)
85.13%
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Validation List (hidden)
Category | Responsible Party
Mechanical | SMS Joy
Electrical | Newcross EP
Wellbore | OMASUP
BHA / Tools | MultiChase
Mud / Solids | Clinton
Cementing | Marine/Logistics
Logistics | TBD
Weather | Fredrikov
HSE | Mega Field
Waiting on Service | Lagrange
Human Error | Ulla
Equipment Failure | Geowell
Wellhead
Other